## Slide 1: Example using PtxGenerator
GAP Analysis Example

## Slide 2: Centralized treasury management
ID_Iniciativa:
Title:
Responsable de la iniciativa:
The integration of the methodology of prioritizing collections in AD depends on the entity defining a collection methodology.
Formal definition of the SAPs of the consolidated system, indicating the operation to be liquidated in each of them, as well as the processes that will be carried out in each of them.
Objective
Risks
ID_GAPS:
Dependencias:
Tasks
Responsable tarea
Tiempo estimado
Recursos estimados
TOTAL
4p - 8p
MT ORG
Defining the SAP structure
GAP001, GAP002, GAP003
INI001
Priority
Complexity
SAP structure
Definition of the account structure. | MF | 02d - 03d | 1p - 2p
Definition of the transaction to be settled in each of the accounts. | MF | 04d - 05d | 1p - 2p
Definition of the payment map. | MF CSC | 04d - 05d | 1p - 2p
Functional account documentation. | ORG | 10d - 15d | 1p - 2p

## Slide 3: Centralized treasury management
ID_Iniciativa:
Title:
Responsable de la iniciativa:
For opening SAPs in the consolidated system, the entity must have its SAP structure defined and it will depend on BoE to carry out.
Operation of the SAPs of the new consolidated system.
Objective
Risks
ID_GAPS:
Dependencias:
Tasks
Responsable tarea
Tiempo estimado
Recursos estimados
TOTAL
13p - 20p
MT SG
Opening SAP in the consolidated system
GAP001, GAP002, GAP003, GAP005, GAP006
INI002
Priority
Complexity
SAP structure
Sending request templates, agents and registration of holders by BdE. | BdE | 01d - 02d | 1p
Preparation of the request to open the RTGS and KLP LCKAs in BoE. | MF | 03d - 04d | 2p - 3p
Registration of KLP codes 11 of the accounts to be opened in the consolidated system. | NI | 03d - 04d | 2p - 3p
Determination of the proxies of the consolidated system accounts. | SG MF | 05d - 06d | 2p - 3p
Completion of the XXXX Bank model of the agents for the opening of the accounts in the consolidated model. | SG MF | 05d – 10d | 2p - 3p
Completion of the xxxx Bank form of registration of account holders. | SG MF | 10d – 15d | 2p - 3p
Verification that the new KLP11 are published in the relationship of direct participants in the System system. | MF | 01d - 01d | 1p - 2p
Finding that the accounts are activated in the consolidated system. | MF | 01d - 01d | 1p - 2p

## Slide 4: Centralized treasury management
ID_Iniciativa:
Title:
Responsable de la iniciativa:
Changing the legal documentation is affected by the opening of SAPs in the consolidated system.
Modification of contracts with linked systems, official market bodies or other relevant documentation that is affected by the new SAP structure.
Objective
Risks
ID_GAPS:
Dependencias:
Tasks
Responsable tarea
Tiempo estimado
Recursos estimados
TOTAL
3p - 5p
MT SG
Adaptation of the entity's legal documentation
GAP004, GAP007
INI003
Priority
Complexity
SAP structure
Definition/Adendas in contracts signed by the entity regarding the settlement of the linked systems. | SG MF | 10d - 15d | 2p - 3p
Signing of the new contracts. | MF | 03d - 04d | 1p - 2p

## Slide 5: Development
ID_Iniciativa:
Title:
Responsable de la iniciativa:
To perform AD adaptation, you have to define the SAP structure of the entity and the user's design of the interface to DT AD .
Adaptation of the internal tool to the new SAP structure.
Objective
Risks
ID_GAPS:
Dependencias:
Tasks
Responsable tarea
Tiempo estimado
Recursos estimados
TOTAL
9p - 17p
AST RA
Adapting AD to the new SAP system
GAP008
INI004
Priority
Complexity
Ad
Review the current configuration of accounts in AD. | DST AD | 02d - 03d | 1p
Definition of display user requirements in AD. | DST AD | 04d - 05d | 1p - 2p
AD interface design. | DST AD | 02d - 03d | 1p - 2p
Set up the new consolidated system accounts in AD. | DST AD | 15d - 20d | 1p - 2p
Adaptation of the parametric tables for suitability to the new matching KLP model. | DST AD | 02d - 03d | 1p - 2p
Definition of the test pool. | DST AD | 02d - 03d | 1p - 2p
Testing account configuration in AD. | DST AD | 01d - 02d | 1p - 2p
Account configuration documentation. | DST AD | 01d – 02d | 1p - 2p
User validation of new accounts configured in AD. | MF | 04d – 05d | 1p - 2p

## Slide 6: Centralized treasury management
ID_Iniciativa:
Title:
Responsable de la iniciativa:
The non-definition of accounting SAPs adapted to the consolidated system and their implementation in the entity's systems.
Adaptation of the accounting APs of the entity to the new SAP structure.
Objective
Risks
ID_GAPS:
Dependencias:
Tasks
Responsable tarea
Tiempo estimado
Recursos estimados
TOTAL
12p - 24p
ORG
Adapting the accounting to the new SAP structure
GAP020
INI005
Priority
Complexity
SAP structure
Defining a ledger account for each of the new accounts in the Consolidated System system. | MF | 05d - 06d | 1p - 2p
Planning of the accounting circuit. | CONT | 01d - 02d | 1p - 2p
Change the ledger accounts in AD, adapting them to the new account structure. | DST AD | 01d - 02d | 1p - 2p
Proof of the change of ledger accounts in AD. | DST AD | 02d - 03d | 1p - 2p
Change of the ledger accounts in the application of directed services, adapting them to the new account structure. | DST | 01d - 02d | 1p - 2p
Evidence of the change of the ledger accounts in the application of direct debit services. | DST | 02d - 03d | 1p - 2p
Change of the ledger accounts in the application of issued transfers, adapting them to the new account structure. | DST | 15d - 20d | 1p - 2p
Proof of the change of the ledger accounts in the application of issued transfers. | DST | 02d - 03d | 1p - 2p
Change of ledger accounts in COMEX, adapting them to the new account structure. | DST | 01d - 02d | 1p - 2p
Proof of the change of ledger accounts in COMEX. | DST | 02d - 03d | 1p - 2p
Change of the ledger accounts in the brokerage application, adapting them to the new account structure. | DST | 01d - 02d | 1p - 2p
Proof of the change of the ledger accounts in the brokerage application. | DST | 02d - 03d | 1p - 2p

## Slide 7: Centralized treasury management
ID_Iniciativa:
Title:
Responsable de la iniciativa:
The adaptation of the calculation of the cash coefficient in AD depends on whether the calculation of the cash coefficient adapted to the consolidated system has been defined and validated.
Update of the Financial Markets policy manual adapting it to the new consolidated system.
Objective
Risks
ID_GAPS:
Dependencias:
Tasks
Responsable tarea
Tiempo estimado
Recursos estimados
TOTAL
11p - 18p
MT
Adaptation of Financial Markets Policies
GAP009
INI006
Priority
Complexity
Policies
Adapting liquidity management principles | MF | 04d - 05d | 1p - 2p
Adaptation of roles and responsibilities in liquidity management. | MF | 04d - 05d | 1p - 2p
Adaptation of the appetite to risk of the entity. | MF | 04d - 05d | 1p - 2p
Adaptation of the reporting and review of its periodicity. | MF | 04d - 05d | 1p - 2p
Adaptation of the procedure for action against the foregoing. | MF | 04d - 05d | 1p - 2p
Validation of liquidity risk management policies and procedures by the steering committee. | MF | 02d – 03d | 3p - 4p
Validation of liquidity risk management policies and procedures by the Board of Directors. | MF | 02d – 03d | 3p - 4p

## Slide 8: Centralized treasury management
ID_Iniciativa:
Title:
Responsable de la iniciativa:
The integration of the methodology of prioritizing collections in AD depends on the entity defining a collection methodology.
Formal definition of the SAPs of the consolidated system, indicating the operation to be liquidated in each of them, as well as the processes that will be carried out in each of them.
Objective
Risks
ID_GAPS:
Dependencias:
Tasks
Responsable tarea
Tiempo estimado
Recursos estimados
TOTAL
4p - 8p
MT ORG
Defining the SAP structure
GAP001, GAP002, GAP003
INI001
Priority
Complexity
SAP structure
Definition of the account structure. | MF | 02d - 03d | 1p - 2p
Definition of the transaction to be settled in each of the accounts. | MF | 04d - 05d | 1p - 2p
Definition of the payment map. | MF CSC | 04d - 05d | 1p - 2p
Functional account documentation. | ORG | 10d - 15d | 1p - 2p

## Slide 9: Centralized treasury management
ID_Iniciativa:
Title:
Responsable de la iniciativa:
For opening SAPs in the consolidated system, the entity must have its SAP structure defined and it will depend on BoE to carry out.
Operation of the SAPs of the new consolidated system.
Objective
Risks
ID_GAPS:
Dependencias:
Tasks
Responsable tarea
Tiempo estimado
Recursos estimados
TOTAL
13p - 20p
MT SG
Opening SAP in the consolidated system
GAP001, GAP002, GAP003, GAP005, GAP006
INI002
Priority
Complexity
SAP structure
Sending request templates, agents and registration of holders by BdE. | BdE | 01d - 02d | 1p
Preparation of the request to open the RTGS and KLP LCKAs in BoE. | MF | 03d - 04d | 2p - 3p
Registration of KLP codes 11 of the accounts to be opened in the consolidated system. | NI | 03d - 04d | 2p - 3p
Determination of the proxies of the consolidated system accounts. | SG MF | 05d - 06d | 2p - 3p
Completion of the XXXX Bank model of the agents for the opening of the accounts in the consolidated model. | SG MF | 05d – 10d | 2p - 3p
Completion of the xxxx Bank form of registration of account holders. | SG MF | 10d – 15d | 2p - 3p
Verification that the new KLP11 are published in the relationship of direct participants in the System system. | MF | 01d - 01d | 1p - 2p
Finding that the accounts are activated in the consolidated system. | MF | 01d - 01d | 1p - 2p

## Slide 10: Centralized treasury management
ID_Iniciativa:
Title:
Responsable de la iniciativa:
Changing the legal documentation is affected by the opening of SAPs in the consolidated system.
Modification of contracts with linked systems, official market bodies or other relevant documentation that is affected by the new SAP structure.
Objective
Risks
ID_GAPS:
Dependencias:
Tasks
Responsable tarea
Tiempo estimado
Recursos estimados
TOTAL
3p - 5p
MT SG
Adaptation of the entity's legal documentation
GAP004, GAP007
INI003
Priority
Complexity
SAP structure
Definition/Adendas in contracts signed by the entity regarding the settlement of the linked systems. | SG MF | 10d - 15d | 2p - 3p
Signing of the new contracts. | MF | 03d - 04d | 1p - 2p

## Slide 11: Development
ID_Iniciativa:
Title:
Responsable de la iniciativa:
To perform AD adaptation, you have to define the SAP structure of the entity and the user's design of the interface to DT AD .
Adaptation of the internal tool to the new SAP structure.
Objective
Risks
ID_GAPS:
Dependencias:
Tasks
Responsable tarea
Tiempo estimado
Recursos estimados
TOTAL
9p - 17p
AST RA
Adapting AD to the new SAP system
GAP008
INI004
Priority
Complexity
Ad
Review the current configuration of accounts in AD. | DST AD | 02d - 03d | 1p
Definition of display user requirements in AD. | DST AD | 04d - 05d | 1p - 2p
AD interface design. | DST AD | 02d - 03d | 1p - 2p
Set up the new consolidated system accounts in AD. | DST AD | 15d - 20d | 1p - 2p
Adaptation of the parametric tables for suitability to the new matching KLP model. | DST AD | 02d - 03d | 1p - 2p
Definition of the test pool. | DST AD | 02d - 03d | 1p - 2p
Testing account configuration in AD. | DST AD | 01d - 02d | 1p - 2p
Account configuration documentation. | DST AD | 01d – 02d | 1p - 2p
User validation of new accounts configured in AD. | MF | 04d – 05d | 1p - 2p

## Slide 12: Centralized treasury management
ID_Iniciativa:
Title:
Responsable de la iniciativa:
The non-definition of accounting SAPs adapted to the consolidated system and their implementation in the entity's systems.
Adaptation of the accounting APs of the entity to the new SAP structure.
Objective
Risks
ID_GAPS:
Dependencias:
Tasks
Responsable tarea
Tiempo estimado
Recursos estimados
TOTAL
12p - 24p
ORG
Adapting the accounting to the new SAP structure
GAP020
INI005
Priority
Complexity
SAP structure
Defining a ledger account for each of the new accounts in the Consolidated System system. | MF | 05d - 06d | 1p - 2p
Planning of the accounting circuit. | CONT | 01d - 02d | 1p - 2p
Change the ledger accounts in AD, adapting them to the new account structure. | DST AD | 01d - 02d | 1p - 2p
Proof of the change of ledger accounts in AD. | DST AD | 02d - 03d | 1p - 2p
Change of the ledger accounts in the application of directed services, adapting them to the new account structure. | DST | 01d - 02d | 1p - 2p
Evidence of the change of the ledger accounts in the application of direct debit services. | DST | 02d - 03d | 1p - 2p
Change of the ledger accounts in the application of issued transfers, adapting them to the new account structure. | DST | 15d - 20d | 1p - 2p
Proof of the change of the ledger accounts in the application of issued transfers. | DST | 02d - 03d | 1p - 2p
Change of ledger accounts in COMEX, adapting them to the new account structure. | DST | 01d - 02d | 1p - 2p
Proof of the change of ledger accounts in COMEX. | DST | 02d - 03d | 1p - 2p
Change of the ledger accounts in the brokerage application, adapting them to the new account structure. | DST | 01d - 02d | 1p - 2p
Proof of the change of the ledger accounts in the brokerage application. | DST | 02d - 03d | 1p - 2p

## Slide 13: Centralized treasury management
ID_Iniciativa:
Title:
Responsable de la iniciativa:
The adaptation of the calculation of the cash coefficient in AD depends on whether the calculation of the cash coefficient adapted to the consolidated system has been defined and validated.
Update of the Financial Markets policy manual adapting it to the new consolidated system.
Objective
Risks
ID_GAPS:
Dependencias:
Tasks
Responsable tarea
Tiempo estimado
Recursos estimados
TOTAL
11p - 18p
MT
Adaptation of Financial Markets Policies
GAP009
INI006
Priority
Complexity
Policies
Adapting liquidity management principles | MF | 04d - 05d | 1p - 2p
Adaptation of roles and responsibilities in liquidity management. | MF | 04d - 05d | 1p - 2p
Adaptation of the appetite to risk of the entity. | MF | 04d - 05d | 1p - 2p
Adaptation of the reporting and review of its periodicity. | MF | 04d - 05d | 1p - 2p
Adaptation of the procedure for action against the foregoing. | MF | 04d - 05d | 1p - 2p
Validation of liquidity risk management policies and procedures by the steering committee. | MF | 02d – 03d | 3p - 4p
Validation of liquidity risk management policies and procedures by the Board of Directors. | MF | 02d – 03d | 3p - 4p